## List of inspection
PROJECT: | Phnom Penh Cambodia Temple
QUALITY DOCUMENT LIST |  |  |  |  | INSPECTION CONSTRUCTION WORKS OF LAND AREA 1 - LAYER 1
Date: | 2024-05-31
STT | Inspection Request N0 | Date of Request | Inspection N0 | Date of Inspection | Subject | Location of land area | Leveling inspection | Date | Compaction Inspection Density test | Date | Density of soil test report | Date | Item | Building | STT | Inspection Request N0 | Date of Request | Inspection N0 | Date of Inspection | Subject | Location of land area | Leveling inspection | Date | Compaction Inspection Density test | Date | Density of soil test report | Date | Item | Building
LAND LEVELING - LEVELING AND COMPACTION INSPECTION
1 | PPCT-INR-LL-01 | 2021-07-25 | PPCT-INP-LL-01 | 2021-07-26 | Land Area 1 - Layer 1 | Axis: B; Ba; C; D; Da - 9; 8 | PPCT-LL-LV-LE01-01 | 2021-07-26 | PPCT-LL-CP-LE-01 | 2021-07-26 | ABC | 2021-07-26 | Land leveling work | Temple Building | 1 | PPCT-INR-LL-01 | 2021-07-25 | PPCT-INP-LL-01 | 2021-07-26 | Land Area 1 - Layer 1 | Axis: B; Ba; C; D; Da - 9; 8 | PPCT-LL-LV-LE01-01 | 2021-07-26 | PPCT-LL-CP-LE-01 | 2021-07-26 | ABC | 2021-07-26 | Land leveling work | Temple Building
2 | PPCT-INR-LL-02 |  | PPCT-INP-LL-02 | [10 empty] | Temple Building
3 | PPCT-INR-LL-03 |  | PPCT-INP-LL-03 | [10 empty] | Ancillary Building |  | Temple Building
4 | PPCT-INR-LL-04 |  | PPCT-INP-LL-04 | [12 empty] | Ancillary Building
5 | PPCT-INR-LL-05 |  | PPCT-INP-LL-05 | [12 empty] | Utilitt Building
6 | PPCT-INR-LL-06 |  | PPCT-INP-LL-06
7 | PPCT-INR-LL-07 |  | PPCT-INP-LL-07 | [12 empty] | LAND LEVELING
8 | PPCT-INR-LL-08 |  | PPCT-INP-LL-08
9 | PPCT-INR-LL-09 |  | PPCT-INP-LL-09 | [12 empty] | Investor | The Association of The Church of Jesus Christ of Latter-day Saints
10 | PPCT-INR-LL-10 |  | PPCT-INP-LL-10 | [12 empty] | Consultant | N/A
11 | PPCT-INR-LL-11 |  | PPCT-INP-LL-11 | [12 empty] | Contractor | Cambodia Branch of Thai Takenaka International Limited
12 | PPCT-INR-LL-12 |  | PPCT-INP-LL-12 | [12 empty] | Project | Phnom Penh Cambodia Temple
13 | PPCT-INR-LL-13 |  | PPCT-INP-LL-13 | [12 empty] | Address | Russian Boulevard, Phnom Penh, Cambodia
14 | PPCT-INR-LL-14 |  | PPCT-INP-LL-14
15 | PPCT-INR-LL-15 |  | PPCT-INP-LL-15
16 | PPCT-INR-LL-16 |  | PPCT-INP-LL-16
17 | PPCT-INR-LL-17 |  | PPCT-INP-LL-17
18 | PPCT-INR-LL-18 |  | PPCT-INP-LL-18
19 | PPCT-INR-LL-19 |  | PPCT-INP-LL-19
20 | PPCT-INR-LL-20 |  | PPCT-INP-LL-20
21 | PPCT-INR-LL-21 |  | PPCT-INP-LL-21
22 | PPCT-INR-LL-22 |  | PPCT-INP-LL-22
23 | PPCT-INR-LL-23 |  | PPCT-INP-LL-23
24 | PPCT-INR-LL-24 |  | PPCT-INP-LL-24
Formulas:
Date of Inspection = [Date of Request]+1
Date of Inspection = VLOOKUP(Q8,[STT]:O35,5,0)
Date = [Date of Inspection]
Date = [Date]
Date of Request = VLOOKUP(Q8,[STT]:O35,3,0)

## Inspection Request
Kingdom of Cambodia
Nation, Religion, King
2021-07-25
DOCUMENT CODE: PPCT-INR-LL-01
CONSTRUCTION WORK INSPECTION REQUEST
|  | Project: | : | Phnom Penh Cambodia Temple
|  | Building: | : | Temple Building
|  | Item | : | Land leveling work
|  | Address | : | Russian Boulevard, Phnom Penh, Cambodia
Respectfully addressed to:
We are contractor have been finished construction works included internal inspection for Land leveling work
| We have requested the…………………………………. |  |  | check and inspect construction works of Land leveling so that we can proceed
next works.
| 1. Subject: | Inspection construction works of Land Area 1 - Layer 1
|  | Location | : | Axis: B; Ba; C; D; Da - 9; 8
Phnom Penh Cambodia Temple Project - Russian Boulevard, Phnom Penh, Cambodia
2. Inspection time:
|  | Start: | : | 9:00 | , | 2021-07-26
|  | End: | : | 11:00 | , | 2021-07-26
|  | Location | : | Phnom Penh Cambodia Temple Project
Russian Boulevard, Phnom Penh, Cambodia
| Received by | [5 empty] | Submit by
| Full name | [5 empty] | Full name
| Date | [5 empty] | Date

## Cons' Inspection
Kingdom of Cambodia
Nation, Religion, King
2021-07-26
DOCUMENT CODE: PPCT-INP-LL-01
CONSTRUCTION WORK INSPECTION
|  |  | Project | : | Phnom Penh Cambodia Temple
|  |  | Building | : | Temple Building
|  |  | Item | : | Land leveling work
|  |  | Address: | : | Russian Boulevard, Phnom Penh, Cambodia
| 1. Subject: |  | Inspection construction works of Land Area 1 - Layer 1
|  |  | Location | : | Axis: B; Ba; C; D; Da - 9; 8
Phnom Penh Cambodia Temple Project - Russian Boulevard, Phnom Penh, Cambodia
2. Inspection members:
| 2.1. | Investor representative
|  | + Mr/Mrs: | [9 empty] | Position:
|  | + Mr/Mrs: | [9 empty] | Position: |  |  |  |  | Hide Data
| 2.2. | Contractor representative: | [13 empty] | Senior Project Manager
+ Mr/Mrs: | [11 empty] | Position: | Construction Manager |  |  | Project Manager
+ Mr/Mrs: | [11 empty] | Position: | Site Engineer |  |  | Construction Manager
Site Manager
| 3. Inspection time: | [14 empty] | Site Engineer
|  |  | Start: | : | 9:00 | , | 2021-07-26
|  |  | End: | : | 11:00 | , | 2021-07-26
|  |  | Location | : | Phnom Penh Cambodia Temple Project - Russian Boulevard, Phnom Penh, Cambodia
4. Work done assessment:
a) Documents attached as a basic for inspection:
- Inspection request of contractors
| - Construction drawing approved by investors and approved modification in design | [14 empty] | TCVN 4447:2012 Earth works - Construction, check and acceptance
| - Soil leveling and compaction inspection sheet | [6 empty] | N0 | : | PPCT-LL-LV-LE01-01 |  |  | Date | : | 2021-07-26
| - Compaction testing report | [6 empty] | N0 | : | PPCT-LL-CP-LE-01 |  |  | Date | : | 2021-07-26
- Standards apply:
| + | TCVN 4447:2012 Earth works - Construction, check and acceptance
| + | ASTM D 1559 Standard test method for density and unit weight of soil in place by the sand-cone method | [13 empty] | TCVN 12791:2020 Standard test method for density of soil in place by the drive - cylinder method
| - Contract No: |  |  | : | [11 empty] | ASTM D 2937-04 Standard test method for density of soil in place by the drive - cylinder method
| - Approved method statement: |  |  | : | [11 empty] | ASTM D 1559 Standard test method for density and unit weight of soil in place by the sand-cone method
- Construction diary and other documents relate to inspecting subject.
b) Construction work quality:
Please see datail in inspection sheet
b1. Soil leveling:
| o | Accept, continue to carry out work.
b2. Compaction - Density test:
| o | Accept, continue to carry out work.
| b3. Density of soil test report: | [6 empty] | N0 | : | ABC |  |  | Date | : | 2021-07-26
| o | Accept, continue to carry out work.
5. Conclusion:
| o | Accept, continue to carry out work.
| o | Accept, with conditions as attachment
| o | Do not accept, reason |  | :
6. Inspection members:
|  | SUB-CON |  |  | TAK ENG | [5 empty] | TAK SM/PM |  |  |  | INVESTOR
Inspection document include:
Construction work inspection and additional document (if any).
Documents attached as a basic for inspection.
Note on C41: Huynh Ngoc Hiep: Choose by drop down list

## Top soil removal
PROJECT: Phnom Penh Cambodia Temple
TOPSOIL REMOVAL CALCULATION SHEET
S. NO. | SURVEY EXISTING LAND LEVEL |  |  |  | AVG. GRID LVL | GFL = TBM +4400 | Removal Depth | Area | Removal Volume
[7 empty] | m | m2 | m3
1 | 1.41 | 2.04 | 1.5 | 2.5 | 1.8625 | 4.015 | 0.2 | 506.8 | 101.36
2 | 2.04 | 2.24 | 2.5 | 2.75 | 2.3825 | 4.015 | 0.2 | 506.8 | 101.36
3 | 2.24 | 3.23 | 2.75 | 3.475 | 2.9238 | 4.015 | 0.2 | 506.8 | 101.36
4 | 3.23 | 4.22 | 3.475 | 4.3 | 3.8062 | 4.015 | 0.2 | 506.8 | 101.36
5 | 4.22 | 4.7 | 4.2 | 4.8 | 4.48 | 4.015 | 0.2 | 506.8 | 101.36
6 | 4.7 | 5.2 | 4.8 | 5.4 | 5.025 | 4.015 | 0.2 | 506.8 | 101.36
7 | 5.2 | 6.5 | 5.4 | 6.45 | 5.8875 | 4.015 | 0.2 | 506.8 | 101.36
8 | 6.5 | 7.8 | 6.45 | 7.5 | 7.0625 | 4.015 | 0.2 | 506.8 | 101.36
9 | 1.5 | 2.5 | 1.51 | 2.37 | 1.97 | 4.015 | 0.2 | 506.8 | 101.36
10 | 2.5 | 2.75 | 2.37 | 2.59 | 2.5525 | 4.015 | 0.2 | 506.8 | 101.36
11 | 2.75 | 3.475 | 2.59 | 3.345 | 3.04 | 4.015 | 0.2 | 506.8 | 101.36
12 | 3.475 | 4.2 | 3.345 | 4.1 | 3.78 | 4.015 | 0.2 | 506.8 | 101.36
13 | 4.2 | 4.8 | 4.1 | 4.82 | 4.48 | 4.015 | 0.2 | 506.8 | 101.36
14 | 4.8 | 5.4 | 4.82 | 5.41 | 5.1075 | 4.015 | 0.2 | 506.8 | 101.36
15 | 5.4 | 6.45 | 5.41 | 6.75 | 6.0025 | 4.015 | 0.2 | 506.8 | 101.36
16 | 6.45 | 7.5 | 6.75 | 8.1 | 7.2 | 4.015 | 0.2 | 506.8 | 101.36
17 | 1.51 | 2.37 | 1.09 | 2.1 | 1.7675 | 4.015 | 0.2 | 506.8 | 101.36
18 | 2.37 | 2.59 | 2.1 | 2.9 | 2.49 | 4.015 | 0.2 | 506.8 | 101.36
19 | 2.59 | 3.345 | 2.9 | 3.75 | 3.1463 | 4.015 | 0.2 | 506.8 | 101.36
20 | 3.345 | 4.1 | 3.75 | 4.9 | 4.0237 | 4.015 | 0.2 | 506.8 | 101.36
21 | 4.1 | 4.82 | 4.9 | 5 | 4.705 | 4.015 | 0.2 | 506.8 | 101.36
22 | 4.82 | 5.41 | 5 | 5.1 | 5.0825 | 4.015 | 0.2 | 506.8 | 101.36
23 | 5.41 | 6.75 | 5.1 | 6.5 | 5.94 | 4.015 | 0.2 | 506.8 | 101.36
24 | 6.75 | 8.1 | 6.5 | 7 | 7.0875 | 4.015 | 0.2 | 506.8 | 101.36
25 | 1.09 | 2.1 | 1.39 | 2.36 | 1.735 | 4.015 | 0.2 | 506.8 | 101.36
26 | 2.1 | 2.9 | 2.36 | 3.17 | 2.6325 | 4.015 | 0.2 | 506.8 | 101.36
27 | 2.9 | 3.75 | 3.17 | 3.5 | 3.33 | 4.015 | 0.2 | 506.8 | 101.36
28 | 3.75 | 4.9 | 3.5 | 4.1 | 4.0625 | 4.015 | 0.2 | 506.8 | 101.36
29 | 4.9 | 5 | 4.1 | 4.6 | 4.65 | 4.015 | 0.2 | 506.8 | 101.36
30 | 5 | 5.1 | 4.6 | 4.9 | 4.9 | 4.015 | 0.2 | 506.8 | 101.36
31 | 5.1 | 6.5 | 4.9 | 6.45 | 5.7375 | 4.015 | 0.2 | 506.8 | 101.36
32 | 6.5 | 7.9 | 6.45 | 8 | 7.2125 | 4.015 | 0.2 | 506.8 | 101.36
Total land area | [7 empty] | 16217.6 | m2
Total topsoil removal volume | [7 empty] | 3243.52 | m3
Total area need to leveling | [7 empty] | 16217.6 | m2
FORMAT SAMPLE

## Back filling & Excavation
PROJECT: Phnom Penh Cambodia Temple
SOIL EXCAVATION & BACKFILLING CALCULATION SHEET
S. NO. | LAND LEVEL AFTER REMOVAL |  |  |  | AVG. GRID LVL | GFL = TBM +4400 | Backfill Depth | Excavation Depth | Area | Backfill Volume | Excavation Volume
[7 empty] | m | m | m2 | m3 | m3
1 | 1.21 | 1.84 | 1.3 | 2.3 | 1.6625 | 4.015 | -2.3525 | - | 506.8 | -1192.247
2 | 1.84 | 2.04 | 2.3 | 2.55 | 2.1825 | 4.015 | -1.8325 | - | 506.8 | -928.711
3 | 2.04 | 3.03 | 2.55 | 3.275 | 2.7237 | 4.015 | -1.2912 | - | 506.8 | -654.4055
4 | 3.03 | 4.02 | 3.275 | 4.1 | 3.6062 | 4.015 | -0.40875 | - | 506.8 | -207.1545
5 | 4.02 | 4.5 | 4 | 4.6 | 4.28 | 4.015 | - | 0.265 | 506.8 |  | 134.302
6 | 4.5 | 5 | 4.6 | 5.2 | 4.825 | 4.015 | - | 0.81 | 506.8 |  | 410.508
7 | 5 | 6.3 | 5.2 | 6.25 | 5.6875 | 4.015 | - | 1.6725 | 506.8 |  | 847.623
8 | 6.3 | 7.6 | 6.25 | 7.3 | 6.8625 | 4.015 | - | 2.8475 | 506.8 |  | 1443.113
9 | 1.3 | 2.3 | 1.31 | 2.17 | 1.77 | 4.015 | -2.245 | - | 506.8 | -1137.766
10 | 2.3 | 2.55 | 2.17 | 2.39 | 2.3525 | 4.015 | -1.6625 | - | 506.8 | -842.555
11 | 2.55 | 3.275 | 2.39 | 3.145 | 2.84 | 4.015 | -1.175 | - | 506.8 | -595.49
12 | 3.275 | 4 | 3.145 | 3.9 | 3.58 | 4.015 | -0.435 | - | 506.8 | -220.458
13 | 4 | 4.6 | 3.9 | 4.62 | 4.28 | 4.015 | - | 0.265 | 506.8 |  | 134.302
14 | 4.6 | 5.2 | 4.62 | 5.21 | 4.9075 | 4.015 | - | 0.8925 | 506.8 |  | 452.319
15 | 5.2 | 6.25 | 5.21 | 6.55 | 5.8025 | 4.015 | - | 1.7875 | 506.8 |  | 905.905 | -11116.658
16 | 6.25 | 7.3 | 6.55 | 7.9 | 7 | 4.015 | - | 2.985 | 506.8 |  | 1512.798
17 | 1.31 | 2.17 | 0.89 | 1.9 | 1.5675 | 4.015 | -2.4475 | - | 506.8 | -1240.393
18 | 2.17 | 2.39 | 1.9 | 2.7 | 2.29 | 4.015 | -1.725 | - | 506.8 | -874.23
19 | 2.39 | 3.145 | 2.7 | 3.55 | 2.9463 | 4.015 | -1.0687 | - | 506.8 | -541.6425
20 | 3.145 | 3.9 | 3.55 | 4.7 | 3.8237 | 4.015 | -0.19125 | - | 506.8 | -96.9255
21 | 3.9 | 4.62 | 4.7 | 4.8 | 4.505 | 4.015 | - | 0.49 | 506.8 |  | 248.332
22 | 4.62 | 5.21 | 4.8 | 4.9 | 4.8825 | 4.015 | - | 0.8675 | 506.8 |  | 439.649
23 | 5.21 | 6.55 | 4.9 | 6.3 | 5.74 | 4.015 | - | 1.725 | 506.8 |  | 874.23
24 | 6.55 | 7.9 | 6.3 | 6.8 | 6.8875 | 4.015 | - | 2.8725 | 506.8 |  | 1455.783
25 | 0.89 | 1.9 | 1.19 | 2.16 | 1.535 | 4.015 | -2.48 | - | 506.8 | -1256.864
26 | 1.9 | 2.7 | 2.16 | 2.97 | 2.4325 | 4.015 | -1.5825 | - | 506.8 | -802.011 |  | 3.7181
27 | 2.7 | 3.55 | 2.97 | 3.3 | 3.13 | 4.015 | -0.885 | - | 506.8 | -448.518
28 | 3.55 | 4.7 | 3.3 | 3.9 | 3.8625 | 4.015 | -0.1525 | - | 506.8 | -77.287 |  | 2.91
29 | 4.7 | 4.8 | 3.9 | 4.4 | 4.45 | 4.015 | - | 0.435 | 506.8 |  | 220.458
30 | 4.8 | 4.9 | 4.4 | 4.7 | 4.7 | 4.015 | - | 0.685 | 506.8 |  | 347.158 | 4.6038
31 | 4.9 | 6.3 | 4.7 | 6.25 | 5.5375 | 4.015 | - | 1.5225 | 506.8 |  | 771.603
32 | 6.3 | 7.7 | 6.25 | 7.8 | 7.0125 | 4.015 | - | 2.9975 | 506.8 |  | 1519.133
Total land area | [9 empty] | 16217.6 | m2
Total back fill volume | [9 empty] | -11116.658 | m3
Total excavation volume | [9 empty] | 11717.216 | m3
Total compaction area (2 layer. Thk-300) | [9 empty] | 1013.6 | m2
Total compaction area ( 1 layer) | [9 empty] | 15204 | m2
Total leveling area | [9 empty] | 16217.6 | m2
FORMAT SAMPLE

## Soil leveling
PROJECT : | Phnom Penh Cambodia Temple | [13 empty] | PROJECT | Phnom Penh Cambodia Temple
[17 empty] | NOTE: | PLEASE DON'T CHANGE THE FORMAT (BORDER - FONT -SIZE) AND CONTENTS
WITHOUT ANY CONFIRM TO MANAGER
SOIL LEVEL CHECKING REPORT | [14 empty] | KEY PLAN
Date | 2021-07-26
Building | Temple Building
Item: | Land leveling work |  |  |  | Subject | Land Area 1 - Layer 1
Location: | Axis: B; Ba; C; D; Da - 9; 8
Point | Designed | Actual | Different | Judgment | Point | Designed | Actual | Different | Judgment | Point | Designed | Actual | Different | Judgment
No. | level (mm) | level (mm) | (mm) |  | No. | level (mm) | level (mm) | (mm) |  | No. | level (mm) | level (mm) | (mm)
1 |  |  |  |  | 20 |  |  |  |  | 39
2 |  |  |  |  | 21 |  |  |  |  | 40
3 |  |  |  |  | 22 |  |  |  |  | 41
4 |  |  |  |  | 23 |  |  |  |  | 42
5 |  |  |  |  | 24 |  |  |  |  | 43
6 |  |  |  |  | 25 |  |  |  |  | 44
7 |  |  |  |  | 26 |  |  |  |  | 45
8 |  |  |  |  | 27 |  |  |  |  | 46
9 |  |  |  |  | 28 |  |  |  |  | 47
10 |  |  |  |  | 29 |  |  |  |  | 48
11 |  |  |  |  | 30 |  |  |  |  | 49
12 |  |  |  |  | 31 |  |  |  |  | 50
13 |  |  |  |  | 32 |  |  |  |  | 51
14 |  |  |  |  | 33 |  |  |  |  | 52
15 |  |  |  |  | 34 |  |  |  |  | 53
16 |  |  |  |  | 35 |  |  |  |  | 54
17 |  |  |  |  | 36 |  |  |  |  | 55
18 |  |  |  |  | 37 |  |  |  |  | 56
19 |  |  |  |  | 38 |  |  |  |  | 57
[7 empty] | SUB-CON |  | TKVN ENG |  | TAK CM |  | INVESTOR

## Density of soil test (Cylinder)
PROJECT: Phnom Penh Cambodia Temple
TCVN 447:2012
SUB-CON: |  |  | LOCATION |  |  |  |  | PART: No |  | Soil Application: Clay,
STANDARD TEST METHOD FOR DENSITY OF SOIL IN PLACE BY THE DRIVE-CYLINDER METHOD |  |  | LAYER |  |  |  |  | LAYER-01
LOCATION EXPLANATION |  |  | PROCTOR TEST NO. |  |  |  |  | TEST-1
MARKING PART PLAN |  |  | DATE OF TEST |  |  |  |  | 2019-01-08
|  |  | MAXIMUM DRY DENSITY(Ymdd) ( LAB) |  | TCVN 12790:2020 | ASTM-D698 |  | 1.62 |  | Khối lượng thể tích khô lớn nhất ( Xác định trong phòng thí nghiệm) TCN 135-2005 cohesive soils & TCVN 8721 - 2012 (non-cohesive)
|  |  | OPTIMUM MOISTURE CONTENT(OMC) | [6 empty] | Độ ẩm tốt nhất (( Xác định trong phòng thí nghiệm): TCN 135-2005 cohesive soils & TCVN 8721-2012 (non-cohesive soils)
{BY STANDARD PROCTOR TEST (LAB)}
|  |  | S. NO. | DESCRIPTION |  | UNIT | SAMPLE 1 | SAMPLE 2 | SAMPLE 3
|  |  | 1 | MASS OF THE CYLINDER (M2) |  | g | 145.5 | 145.5 | 145.5 | Khối lượng dao
|  |  | 2 | MASS OF THE CYLINDER AND WET SOIL SAMPLE M1 |  | g | 481.4 | 481.4 | 481.4 | Khối lượng dao + mẫu đất
|  |  | 3 | VOLUME OF THE CYLINDER (V) |  |  | 200 | 200 | 200 | Thể tích dao vòng
|  |  | 4 | MASS OF THE WET SOIL (M=M1-M2) |  | g | 335.9 | 335.9 | 335.9 | Khối lượng của mẫu đất
|  |  | 5 | WT OF SOIL +ALUMINUM BOX (M1) |  | g | 111.8 | 111.8 | 111.8 | Khối lượng của mẫu đất + hộp nhôm
|  |  | 6 | WT OF DRYED SOIL +ALUMINUM BOX (M2) |  | g | 107.4 | 107.4 | 107.4 | Khối lượng của mẫu đất đã sấy khô + hộp nhôm
|  |  | 7 | WT OF ALUMINUM BOX (MB) |  | g | 61.3 | 61.3 | 61.3 | Khối lượng của hộp nhôm
|  |  | 8 | MOISTURE CONTENT (W) |  | % | 9.5445 | 9.5445 | 9.5445 | Độ ẩm của mẫu đất ( Theo tính toán)
|  |  | 9 | THE DRY MASS OF THE SOIL SAMPLE (M3) |  | g | 306.6335 | 306.6335 | 306.6335 | Độ ẩm của mẫu đất ( Đo bằng dụng cụ đo độ ẩm)
|  |  | 10 | BULK DENSITY (gw=W/V) |  | g/cm3 | 1.6795 | 1.6795 | 1.6795 | Khối lượng thể tích tự nhiên của đất thí nghiệm
|  |  | 11 | DRY DENSITY: gK=gW/(1+0.01W) | / M3/V | g/cm3 | 1.5332 | 1.5332 | 1.5332 | Khối lượng thể tích khô của đất thí nghiệm
|  |  | 12 | MAXIMUM DRY DENSITY (MDD) |  | g/cm3 | 1.62 | 1.62 | 1.62 | Khối lượng thể tích khô lớn nhất ( Xác định trong phòng thí nghiệm)
|  |  | 13 | COMPACTION PERCENTAGE |  | % | 94.64 | 94.64 | 94.64
|  |  |  | AVG. COMPACTION % |  | % | 94.64
|  |  | AS PER | ASTM D 2937-04
|  |  | Sub-Con Name |  | TAKENAKA |  | TAKENAKA
METHOD | AS PER TCVN 4447:2012 | Frequency:1 test/500m2 ~ 1000m2 | CONCERN BY |  | PREPARED BY |  | APPROVED BY
|  |  | ENGINEER |  | ENGINEER (TAK) |  | CONSTRUCTION MANAGER (TAK)
FORMAT OF
SOIL/AGGEGATES COMPACTION TESTING RECORD
Note on O8: Huynh Ngoc Hiep: Result from LAB
Note on K28: Huynh Ngoc Hiep: Choose applicable standard

## Density of soil test (Sandcone)
PROJECT | : | Phnom Penh Cambodia Temple
[6 empty] | LOCATION: | [5 empty] | PART: |  |  |  | NOTE: | PLEASE DON'T CHANGE THE FORMAT (BORDER - FONT -SIZE) AND CONTENTS
SUB-CON | : |  |  |  | LAB | LAYER | [5 empty] | FOUNDATION PIT |  |  |  |  | WITHOUT ANY CONFIRM TO MANAGER
STANDARD TEST METHOD FOR DENSITY OF SOIL IN PLACE BY THE SAND -CONE METHOD | [5 empty] | TEST N0. | [5 empty] | TEST-1
LOCATION EXPLANATION: CAR PARKING AREA | [5 empty] | DATE OF TEST | [5 empty] | 2024-05-31
[6 empty] | MAXIMUM DRY DENSITY(Ymdd) (LAB) | [5 empty] | 1.8167 | g/cm3
[6 empty] | OPTIMUM MOISTURE CONTENT(OMC) | [5 empty] | 7.7833 | % |  |  | Khối lượng thể tích khô lớn nhất ( Xác định trong phòng thí nghiệm) TCN 135-2005 cohesive soils & TCVN 8721 - 2012 (non-cohesive)
[6 empty] | {BY STANDARD PROCTOR TEST (LAB)} | [9 empty] | Độ ẩm tốt nhất (( Xác định trong phòng thí nghiệm): TCN 135-2005 cohesive soils & TCVN 8721-2012 (non-cohesive soils)
[6 empty] | S. NO. | DESCRIPTION |  |  | UNIT | SAMPLE 1 | SAMPLE 2 | SAMPLE 3
[6 empty] | 1 | SOIL FROM THE TEST HOLE | WT OF SOIL + TRAY |  | g | 2126 | 2364 |  | Mw |  | Khối lượng mẫu ướt và khay
[6 empty] | 2 |  | WT OF TRAY |  | g | 158 | 158 |  |  |  | Khối lượng của khay
[6 empty] | 3 |  | MOIST MASS OF THE SOIL |  | g | 1968 | 2206 |  |  |  | Khối lượng của mẫu ướt
[6 empty] | 4 |  | DRY MASS OF THE SOIL |  | g | 1812.2132 | 2025.9904 |  |  |  | Khối lượng của mẫu khô (Lấy mẫu ướt sấy khô - Lấy 1 lượng nhỏ hơn lượng mẫu ướt, xác định được độ ẩm. Từ đó tính ra khối lượng khô của mẫu đất)
[6 empty] | 5 | SAND & TOOL FOR TESTING | WT OF SAND + TOOL ( BEFORE TEST):"A" |  | g | 10460 | 10346 |  | A | (g) | Khối lượng của cát và bộ dụng cụ trước khi thí nghiệm |  |  |  | Khối lượng bộ phễu có chứa cát chuẩn trước khi thí nghiệm, g
[6 empty] | 6 |  | WT OF SAND + TOOL ( AFTER TEST): "B" |  | g | 7203 | 6920 |  | B | (g) | Khối lượng của cát và bộ dụng cụ sau thí nghiệm
[6 empty] | 7 |  | WT OF SAND + CONE + PLATE: "C" |  | g | 1750 | 1750 |  | C | (g) | Khối lượng cát trong cone + đế
[6 empty] | 8 |  | WT OF SAND IN: CONE + PLATE + TEST HOLE |  | g | 3257 | 3426 |  |  |  | Khối lượng cát trong cone + đế + hố đào
[6 empty] | 9 |  | BULK DENISITY OF THE SAND "g" |  | g/cm3 | 1.45 | 1.45 |  |  |  | Khối lượng thể tích của cát
[6 empty] | 10 |  | WT OF SAND IN TEST HOLE |  | g | 1507 | 1676 |  |  |  | Khối lượng của cát trong hố đào
[6 empty] | 11 |  | VOLUME OF TEST HOLE |  | cm3 | 1039.3103 | 1155.8621 |  | Vh | (cm3) | Thể tích hố đào
[6 empty] | 12 | MOISTURE CONTENT | WT OF SAMPLE + TRAY "D" |  | g | 467.5 | 470.5 |  | D |  | Khối lượng mẫu ướt và khay
[6 empty] | 13 |  | WT OF DRY SAMPLE + TRAY "E" |  | g | 443 | 445 |  | E |  | Khối lượng mẫu khô và khay
[6 empty] | 14 |  | WT OF TRAY "F" |  | g | 158 | 158 |  | F |  | Khối lượng của khay
[6 empty] | 15 |  | WT OF DRY SAMPLE |  | g | 285 | 287 |  |  |  | Khối lượng mẫu khô
[6 empty] | 16 |  | MOISTURE CONTENT (Wtt) |  | % | 8.5965 | 8.885 |  | Wtt |  | Đô ẩm của mẫu
[6 empty] | 17 | WET DENSITY OF THE TESTED SOIL gktt |  |  | g/cm3 | 1.8936 | 1.9085 |  |  |  | Khối lượng thể tích khô của mẫu trong hố đào
[6 empty] | 18 | DRY DENSITY OF THE TESTED SOIL gktt |  |  | g/cm3 | 1.7437 | 1.7528 |  |  |  | Khối lượng thể tích khô
[6 empty] | 19 | COMPACTION "K" |  |  | % | 95.9818 | 96.4842 |  |  |  | Hệ số đầm chặt
[6 empty] | 20 | AVG. COMPACTION % |  |  | % |  | 96.233
AS PER ASTM D 1556
DENSITY OF SAND ( APPENDIX B - 22 TCN 346-06)
[6 empty] | SUB - CON |  |  | TAKENAKA |  | TAKENAKA VIETNAM |  |  |  |  | Xác đinh khối lượng thể tích của cát chuẩn
[16 empty] | WT of sand + cylinder/ Khối lượng thùng đong và cát |  | m3 | g
[16 empty] | WT on cylinder |  | m4 | g
[16 empty] | Voulume of cylinder |  | Vc | cm3
SOIL | [15 empty] | Density of sand ( 3 test times) |  | g | g/cm3
METHOD | : | FIELD DENSITY BY SAND CONE METHOD |  | Frequency:1 test/500m2 ~ 1000m2 |  | CONCERN BY |  |  | APPROVED BY |  | APPROVED BY
[6 empty] | ENGINEER (SUB-CON) |  |  | ENGINEER (TAK) |  | MANAGER (TAK)
|  |  | SOIL | Frequency:1 test/500m2 ~ 1000m2 | [11 empty] | WT OF SAND + CONE + PLATE "C" ( APPENDIX A - 22 TCN 346-060
Xác định khối lượng của cát chuẩn chứa trong phểu và đế định vị của bộ khung
|  |  | AGGREGATES | Frequency: 1 Test/ 100m2 TCVN8859_2011 Graded Aggregate Bases and Subbases Pavement | [11 empty] | Xác định khối lượng ban đầu của bộ phểu rót cát có chứa cát |  |  | m1 | g
[16 empty] | Xác định khối lượng bộ phễu rót cát và cát còn lại |  |  | m2 | g
[16 empty] | Khối lượng của cát trong phễu và đế |  |  | C = m1-m2
K
K=(100𝑘𝑡𝑡)/𝑉𝑐
SAMPLE 02
SAMPLE 01
FORMAT OF
SOIL/AGGEGATES COMPACTION TESTING RECORD
Note on Q6: Huynh Ngoc Hiep: In LAB - GSL - 180119